## 2025 2026 Procurement
ANNEXURE A
Name of National Department/Institution |  |  | DEPARTMENT OF SMALL BUSINESS DEVELOPMENT
Director-General |  |  | THULISILE MANZINI
Director SCM: |  |  | IAN CHABALALA
Telephone number and email address: |  |  | (012) 394 5258
Due Date: Date: 31 MARCH 2026
|  | TManzini@dsbd.gov.za | (012) 394 5258 | [13 empty] | 16028000
TABLE 1 | [11 empty] | Planned dates (week ending) - YYMMDD
|  |  | 80300000 |  | 0 |  | 0 | 41800000 | 23200000 | 15300000
No | Programme | Project Description | Estimated Value (incl, taxes) | Source of Fundng | Earmarked Funded or Not Earmarked | Good and Service or Major or Minor Assets | 2025/26 "R" | 2026/27 "R" | 2027/28 "R" | 2028/29 R | Method of procurement | Bid Specification | Approved Evaluation Criteria | Advert | Bid closing | Bid award | Value of Contract | Contract commence | Contract expiry
1 | Programme 1 | Appointment of a service provider to render an Events Management Services, Stakeholder Engagement, and Outreach Campaigns to the Department of Small Business Development (DSBD) for a period of three years (36 months) on “an as and when required basis”. | 13500000 | Voted | YES |  | 0 | 2500000 | 5000000 | 6000000 | Open Tender | 2025-10-20 | 2025-10-27 | 2025-11-20 | 2025-12-19 | 2026-04-17 | 2025-12-08 | 2026-05-01 | 2028-04-30
2 | Programme 1 | Procurement of Departmental Laptops. | 5100000 | Voted | NO | YES | 0 | 1600000 | 1700000 | 1800000 | Predefined SITA ICT Procurement | N/A | N/A | N/A | N/A | 2026-07-31 | 6000000 | 2026-07-31 | 2026-09-30
3 | Programme 1 | Appointment of the suitable service provider to assist the Department with response handling (receiving and sifting of the application of employment). | 550000 | Voted | NO |  | 0 | 550000 | 0 | 0 | Open RFQ | 2025-11-11 | 2026-02-06 | 2026-02-06 | 2026-02-27 | 2026-04-10 | 2026-03-01 | 2026-05-01 | 2028-04-30
4 | Programme 1 | The appointment of a suitable service provider(s) to assist DSBD with the (Media Buying and Advertising Procurement), radio and television airtime. Is it only billboard advertising, check with Communications if the agreement with Sedfa will not assist with this. | 12500000 | Voted | YES |  | 0 | 3500000 | 9000000 | 0 | Procure using other means | N/A | N/A | N/A | N/A | 2026-05-01 | 2000000 | 2026-05-01 | 2027-03-31
5 | Programme 1 | The appointment of a suitable service provider to assist DSBD with the Mobile Bus (OB Van). | 2500000 | Voted | YES |  | 0 | 2500000 | 0 | 0 | Open Tender | N/A | N/A | N/A | N/A | 2026-07-03 | 2026-11-30 | 2026-08-03 | 2027-03-31
6 | Programme 1 | The appointment of a suitable service provider(s) to assist DSBD with the provision of public relations and marketing management | 9200000 | Voted | YES |  | 0 | 9200000 |  | 0 | Open Tender | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-29 | 2026-07-01 | 2000000 | 2026-08-01 | 2027-03-31
7 | Programme 1 | Appointment of a Service provider to supply and deliver Pool vehicles. | 4500000 | Voted | NO | YES | 0 | 1500000 | 1500000 | 1500000 | RT57 Transversal Contract | N/A | N/A | 2026-04-10 | 2026-05-04 | 2026-05-08 |  | 2026-05-08 | 2027-08-31
8 | Programme 2 | Appointment of a service provider to compile the One National Plan for the MSMS ecosystem in South Africa for the coordination of sectors that are prioritised for the benefit of small enterprises that are operating in various sectors of the economy, for job creation. | 4000000 | Voted | YES |  | 0 | 4000000 | 0 | 0 | Open Tender | 2025-12-20 | 2026-01-13 | 2026-02-20 | 2026-03-13 | 2026-04-24 |  | 2026-05-01 | 2026-08-31
9 | Programme 2 | Appointment of a service provider to assist with data collection instruments, software/tools for data collection, analysis, and capacity-building training required to support research and evaluation studies for the upcoming financial year. | 950000 | Voted | YES |  | 0 | 950000 | 0 | 0 | Open RFQ | 2026-04-20 | 2026-04-27 | 2026-05-05 | 2026-05-29 | 2026-06-19 | 2026-06-01 | 2026-08-01 | 2027-03-31
10 | Programme 3 | Appointment of a multi-disciplinary consulting firm to provide engineering and architectural firms to assess capital equipment and machinery and/or processes, infrastructure and associated costs such as design, build related to DSBD supported projects related to Business Infrastructure support programme for the period of 3 Years | 18000000 | Voted | YES |  | 0 | 6000000 | 6000000 | 6000000 | Open Tender | 2026-04-20 | 2026-04-30 | 2026-05-01 | 2026-05-31 | 2026-06-11 |  | 2026-07-31 | 2029-08-31
11 | Programme 3 | The appointment of a suitable service provider to partner with for the support of SMME'S to gain greater access to markets | 2000000 | Voted | YES |  | 0 | 2000000 | 0 | 0 | Deviation: Partnership Proudly South African | N/A | N/A | N/A | N/A | 2026-06-05 | 2026-04-01 | 2026-06-05 | 2027-03-31
12 | Programme 3 | The appointment of a suitable service provider to assist DSBD with providing conference facilities and venue for hosting the International Cooperatives Day (ICD) | 1000000 | Voted | YES |  | 0 | 1000000 | 0 | 0 | Open Tender | N/A | N/A | N/A | N/A | 2026-06-30 | 2000000 | 2026-07-01 | 2027-03-31
13 | Programme 4 | The procurement of a Case Management System (CMS) to enable for recording, processing, reviewing, monitoring and evaluating performance. | 2000000 | Voted | YES |  | 0 | 2000000 | 0 | 0 | Open Tender | 2025-10-28 | 2025-11-06 | 2025-11-14 | 2025-12-19 | 2027-02-19 | 2027-03-01 | 2028-02-28 | 2028-02-28
14 | Programme 4 | The appointment of a suitable service provider to assist DSBD with the procurement of Office Space contingency for the establish the Ombuds Office. | 1000000 | Voted | YES |  | 0 | 1000000 | 0 | 0 | Open Tender | 2025-10-28 | 2025-11-06 | 2025-11-14 | 2025-12-19 | 2027-02-19 | 2025-10-01 | 2027-03-01 | 2028-02-28
15 | Programme 4 | The appointment of a suitable service provider to provide conference facilities and a venue the hosting of the MSME Summit in November 2026. | 500000 | Voted | YES |  | 0 | 500000 | 0 | 0 | Open RFQ | N/A | N/A | N/A | N/A | 2026-09-18 | 2026-11-30 | 2026-11-30 | 2026-11-30
16 | Programme 4 | The appointment of a suitable service provider to provide conference facilities and a venue for hosting the presidential MSME and Cooperate Awards in November 2026. | 3000000 | Voted | YES |  | 0 | 3000000 | 0 | 0 | Open RFQ | N/A | N/A | N/A | N/A | 2026-09-18 | 2025-10-01 | 2026-11-30 | 2026-11-30
The Accounting Officer/ Authority declares that he/she has engaged with the Executive Authority who concurs with and has approved this Procurement Plan.
Accounting Officer / Authority Signature
Date